## April
Date | Day | S.No | Name of the User | e-mail | Name of the Task / Item | Start Date | End Date | Status | Remarks | Review | Last modified by
2025-04-15 | Tuesday | 1
2
3
4
5
6
7
8
9
10
2025-04-16 | Wednesday | 1
2
3
4
5
6
7
8
9
10
2025-04-17 | Thursday | 1
2
3
4
5
6
7
8
9
10
2025-04-18 | Friday | 1 |  |  | Project Initialization, Create Repo, Setup Environment
2
3
4
5
6
7
8
9
10
2025-04-19 | Saturday | 1 |  |  | Create Landing Page Wireframe
2
3
4
5
6
7
8
9
10
2025-04-20 | Sunday | 1 |  |  | Build Navbar, Footer Components
2
3
4
5
6
7
8
9
10
2025-04-21 | Monday | 1 |  |  | Implement Hero Section with CTA
2
3
4
5
6
7
8
9
10
2025-04-22 | Tuesday | 1 |  |  | Add Featured Products Section
2
3
4
5
6
7
8
9
10
2025-04-23 | Wednesday | 1 |  |  | ntegrate Testimonials or Reviews Snippet
2
3
4
5
6
7
8
9
10
2025-04-24 | Thursday | 1 |  |  | Add Contact Section + Map Embed
2
3
4
5
6
7
8
9
10
2025-04-25 | Friday | 1 |  |  | Make Page Responsive (Mobile, Tab)
2
3
4
5
6
7
8
9
10
2025-04-26 | Saturday | 1 |  |  | SEO, Meta Tags, Basic Accessibility Fixes
2
3
4
5
6
7
8
9
10
2025-04-27 | Sunday | 1 |  |  | Test and Finalize Landing Page
2
3
4
5
6
7
8
9
10
2025-04-28 | Monday | 1 |  |  | Setup Product Database Schema
2
3
4
5
6
7
8
9
10
2025-04-29 | Tuesday | 1 |  |  | Create Product Listing Page (Grid Layout)
2
3
4
5
6
7
8
9
10
2025-04-30 | Wednesday | 1 |  |  | Build Product Detail Page Structure
2
3
4
5
6
7
8
9
10

## May
Date | Day | S.No | Name of the User | e-mail | Name of the Task / Item | Start Date | End Date | Status | Remarks | Review | Last modified by
2025-05-01 | Thursday | 1 |  |  | Add "3D View" Integration (Static)
2
3
4
5
6
7
8
9
10
2025-05-02 | Friday | 1 |  |  | Build “Try-On” UI Component
2
3
4
5
6
7
8
9
10
2025-05-03 | Saturday | 1 |  |  | Integrate AR SDK/Mock Try-On System
2
3
4
5
6
7
8
9
10
2025-05-04 | Sunday | 1 |  |  | Connect Product Page with DB
2
3
4
5
6
7
8
9
10
2025-05-05 | Monday | 1 |  |  | Add Filters (Category, Price, Popularity)
2
3
4
5
6
7
8
9
10
2025-05-06 | Tuesday | 1 |  |  | Implement “Available for Rent/Sale” Toggle
2
3
4
5
6
7
8
9
10
2025-05-07 | Wednesday | 1 |  |  | Show Stock Info & Availability
2
3
4
5
6
7
8
9
10
2025-05-08 | Thursday | 1 |  |  | Add Review Ratings on Product Page
2
3
4
5
6
7
8
9
10
2025-05-09 | Friday | 1 |  |  | Create Add-to-Cart Functionality
2
3
4
5
6
7
8
9
10
2025-05-10 | Saturday | 1 |  |  | Build "Compare Product" Feature
2
3
4
5
6
7
8
9
10
2025-05-11 | Sunday | 1 |  |  | UI Enhancements & Mobile Compatibility
2
3
4
5
6
7
8
9
10
2025-05-12 | Monday | 1 |  |  | Testing and Debugging Product Pages
2
3
4
5
6
7
8
9
10
2025-05-13 | Tuesday | 1 |  |  | Build Cart Page UI
2
3
4
5
6
7
8
9
10
2025-05-14 | Wednesday | 1 |  |  | Add Quantity Update + Remove Buttons
2
3
4
5
6
7
8
9
10
2025-05-15 | Thursday | 1 |  |  | Implement Cart DB Connection
2
3
4
5
6
7
8
9
10
2025-05-16 | Friday | 1 |  |  | Apply Promo Code Mechanism
2
3
4
5
6
7
8
9
10
2025-05-17 | Saturday | 1 |  |  | Integrate Offer Algorithm (Rules-based)
2
3
4
5
6
7
8
9
10
2025-05-18 | Sunday | 1 |  |  | Create Checkout Page Design
2
3
4
5
6
7
8
9
10
2025-05-19 | Monday | 1 |  |  | Add Address & Payment Info UI
2
3
4
5
6
7
8
9
10
2025-05-20 | Tuesday | 1 |  |  | Simulate Payment Gateway (Mock)
2
3
4
5
6
7
8
9
10
2025-05-21 | Wednesday | 1 |  |  | Display Order Summary + Invoice
2
3
4
5
6
7
8
9
10
2025-05-22 | Thursday | 1 |  |  | Test Full Cart Flow
2
3
4
5
6
7
8
9
10
2025-05-23 | Friday | 1 |  |  | Dashboard Wireframe
2
3
4
5
6
7
8
9
10
2025-05-24 | Saturday | 1 |  |  | Setup Charts (Sales, User, Feedback)
2
3
4
5
6
7
8
9
10
2025-05-25 | Sunday | 1 |  |  | Show Product View Stats
2
3
4
5
6
7
8
9
10
2025-05-26 | Monday | 1 |  |  | Track User Session Duration
2
3
4
5
6
7
8
9
10
2025-05-27 | Tuesday | 1 |  |  | Visualize Rental vs. Purchase Trends
2
3
4
5
6
7
8
9
10
2025-05-28 | Wednesday | 1 |  |  | Include Feedback Report Panel
2
3
4
5
6
7
8
9
10
2025-05-29 | Thursday | 1 |  |  | Dynamic Filtering in Dashboard
2
3
4
5
6
7
8
9
10
2025-05-30 | Friday | 1 |  |  | Admin-only Access Config
2
3
4
5
6
7
8
9
10
2025-05-31 | Saturday | 1 |  |  | Style Dashboard for Mobile View
2
3
4
5
6
7
8
9
10

## June
Date | Day | S.No | Name of the User | e-mail | Name of the Task / Item | Start Date | End Date | Status | Remarks | Review | Last modified by
2025-06-01 | Sunday | 1 |  |  | Test and Fix Dashboard Bugs
2
3
4
5
6
7
8
9
10
2025-06-02 | Monday | 1 |  |  | Admin Login Page + Auth Setup
2
3
4
5
6
7
8
9
10
2025-06-03 | Tuesday | 1 |  |  | Product Add/Edit/Delete Interface
2
3
4
5
6
7
8
9
10
2025-06-04 | Wednesday | 1 |  |  | Order Management Panel
2
3
4
5
6
7
8
9
10
2025-06-05 | Thursday | 1 |  |  | Offers & Coupons Management
2
3
4
5
6
7
8
9
10
2025-06-06 | Friday | 1 |  |  | View Users, Transactions Logs
2
3
4
5
6
7
8
9
10
2025-06-07 | Saturday | 1 |  |  | Update Access Roles
2
3
4
5
6
7
8
9
10
2025-06-08 | Sunday | 1 |  |  | Secure Panel + Testing
2
3
4
5
6
7
8
9
10
2025-06-09 | Monday | 1 |  |  | Collect Review Dataset (Sample)
2
3
4
5
6
7
8
9
10
2025-06-10 | Tuesday | 1 |  |  | Preprocess Reviews (Stopwords, Lemmas)
2
3
4
5
6
7
8
9
10
2025-06-11 | Wednesday | 1 |  |  | Train Sentiment Model (Naive Bayes / SVM)
2
3
4
5
6
7
8
9
10
2025-06-12 | Thursday | 1 |  |  | Test Model Accuracy & Save
2
3
4
5
6
7
8
9
10
2025-06-13 | Friday | 1 |  |  | Create Review UI Section
2
3
4
5
6
7
8
9
10
2025-06-14 | Saturday | 1 |  |  | Integrate Model to Classify Reviews
2
3
4
5
6
7
8
9
10
2025-06-15 | Sunday | 1 |  |  | Add “Flagged” Reviews for Admin Check
2
3
4
5
6
7
8
9
10
2025-06-16 | Monday | 1 |  |  | Finalize & Deploy Review Filtering
2
3
4
5
6
7
8
9
10
2025-06-17 | Tuesday | 1 |  |  | User Signup/Login UI + Firebase/Auth Setup
2
3
4
5
6
7
8
9
10
2025-06-18 | Wednesday | 1 |  |  | Forgot Password + OTP
2
3
4
5
6
7
8
9
10
2025-06-19 | Thursday | 1 |  |  | Profile Page + Edit Profile
2
3
4
5
6
7
8
9
10
2025-06-20 | Friday | 1 |  |  | Track Orders, Wishlist, History
2
3
4
5
6
7
8
9
10
2025-06-21 | Saturday | 1 |  |  | Admin Access Toggle for Special Users
2
3
4
5
6
7
8
9
10
2025-06-22 | Sunday | 1 |  |  | Final User Module Testing
2
3
4
5
6
7
8
9
10
2025-06-23 | Monday | 1 |  |  | Cross-module Linking (Cart ↔ Offers, etc.)
2
3
4
5
6
7
8
9
10
2025-06-24 | Tuesday | 1 |  |  | Final UI/UX Review & Cleanup
2
3
4
5
6
7
8
9
10
2025-06-25 | Wednesday | 1 |  |  | Run Lighthouse + Performance Audit
2
3
4
5
6
7
8
9
10
2025-06-26 | Thursday | 1 |  |  | Security Testing
2
3
4
5
6
7
8
9
10
2025-06-27 | Friday | 1 |  |  | Feedback Round 1
2
3
4
5
6
7
8
9
10
2025-06-28 | Saturday | 1 |  |  | Bug Fixing
2
3
4
5
6
7
8
9
10
2025-06-29 | Sunday | 1 |  |  | Final QA Round
2
3
4
5
6
7
8
9
10
2025-06-30 | Monday | 1 |  |  | Final QA Round
2
3
4
5
6
7
8
9
10

## July
Date | Day | S.No | Name of the User | e-mail | Name of the Task / Item | Start Date | End Date | Status | Remarks | Review | Last modified by
2025-07-01 | Tuesday | 1
2
3
4
5
6
7
8
9
10
2025-07-02 | Wednesday | 1
2
3
4
5
6
7
8
9
10
2025-07-03 | Thursday | 1
2
3
4
5
6
7
8
9
10
2025-07-04 | Friday | 1
2
3
4
5
6
7
8
9
10
2025-07-05 | Saturday | 1
2
3
4
5
6
7
8
9
10
2025-07-06 | Sunday | 1
2
3
4
5
6
7
8
9
10
2025-07-07 | Monday | 1
2
3
4
5
6
7
8
9
10
2025-07-08 | Tuesday | 1
2
3
4
5
6
7
8
9
10
2025-07-09 | Wednesday | 1
2
3
4
5
6
7
8
9
10
2025-07-10 | Thursday | 1
2
3
4
5
6
7
8
9
10